## Slide 1
Open Issues
Planning next week / days
Load pending scheduling agreements (SD-03)
Test matrix: Generate test combinations for every customer - MSG/Material/Scheduling Agreement
Decisions needed
Definition of which messages except Forecast and ASN should be setup for MX (Astrid)
Risks
Not enough time to test all customer-message combinations
Extended post GoLive testing and corrective activities
Major Work Results
Planio update done (December 2021)
SAP HEQ300 done. A few customer numbers need to be updated
Seeburger: Customer numbers and messages are all updated (except a few special message types for single customer)
Overall Status
Week: 51
Date: 03.01.2022
Overall status
SERPRO Rollout MX
Project Status Reporting | EDI 2022 Week 1
1
KPIs
xxx 0%
xxx 0%
xxx 0%
xxx 0%
xxx 0%
xxx 0%
xxx 0%
Lacking viable test plan to meet project schedule deadlines, especially considering projected changes required for ASN
Data availability for technical testing to continue
Pending test combinations for technical testing to continue
Oudated

## Slide 2
EDI Data Readiness for MX - Customers
Object | Total | Loaded | % | Comments
Scheduling agreement (SD-03) | 983 | 65 | 6.6% | Only initial sample loaded for 5 customers
BP SoldTo (FI-02) | 77 | 65 | 84.4% | 
BP ShipTo (FI-02) | 115 | 108 | 93.9% | 
Info record (SD-01) | 840 | 840 | 100% | 
Pricing Conditions (SD-02) | 1084 | 930 | 85% | 154 Duplicates (impact on loading SD-03?)
Inbound/Outbound
Outbound
Object | Total | Loaded | % | Comments
Stock (EWM-02) |  | 0 | 0% | Not ready yet
Packaging (EWM-PS) |  | 0 | 0% | Note ready yet
10.01.2022

## Slide 3
EDI Data Readiness for MX - Vendors
Object | Total | Loaded | % | Comments
Scheduling agreement Purch (MM-04) | 1164 | 1086 | 93% | 
BP Vendor (FI03) | 886 | 886 | 100% | 
Info record (MM-03) | 1175 | 1035 | 88% | 
Source List | ???? | 1035 | 88% | Not a data object depends on MM-03-04, to be generated
Outbound
Inbound
Object | Total | Loaded | % | Comments
Stock (EWM-02) |  | 0 | 0% | Not ready yet
Packaging (EWM-PS) |  | 0 | 0% | Note ready yet
10.01.2022

## Slide 4: EDI MX Project Readiness Steps Overview
No started
Functional Content Test
INBOUND/OUTBOUND
Data availability in SAP
Seeburger / SNP Message Translation
SAP Message Entry SETUP
Individual Msg OK
OK!
Tech. Test
Lead Seeburger = Bertram
Participation SNP = Corinna/Mateusz
Must be loaded in SAP
Scheduling agreement
BP (sold to and ship to)
Info record
Pricing Conditions
INBOUND: Test Messages matching to the provided master data
Functional Content Test
Data available and consistent in SAP
HUF Verification of message correctness (Planio)
OUTBOUND
Data availability in SAP
Must be loaded in SAP
Complete EWM process
Stock
Packaging
Etc.
OUTBOUND: HuF needs to create outbound messages based on the inbound massages just processed.
SAP will send to Seeburger
Rollout Connectivity Test
SNP
Customer = Corinna
Supplier = Mateusz
Lead HUF = Astrid / Lourdes
Participation SNP Business Consultant = Pilar
Lead HUF
Data Availability = Astrid / Lourdes
Participation SNP = Pilar
End to End Functional Content Test
Test for every Customer
Based on Inbound msg create ASN
Check for data completeness and in the correct fields
SNP Tech. Test 40% = SNP finalized